NUVRION

Implementation Plan & Milestone Backlog

Execution Baseline for Nuvrion v0.1

| Document control | Value |
| --- | --- |
| Document ID | NUV-IMP-001 |
| Version | v0.1 |
| Status | Draft — For Review |
| Governing Documents | NUV-PRD-001; NUV-TADS-001; NUV-DAPI-001 |
| Planning Model | 10 milestones; 16 two-week sprints; 32-week baseline |
| Reference Team | 8 core FTE plus fractional security/UX/operations support |
| Classification | Product & Engineering |
| Date | August 2026 |

GOVERNING DELIVERY OBJECTIVE

Deliver a secure, testable Nuvrion v0.1 through gated vertical slices, proving the platform and VMware path first, then adding Workstation, AWS, and Azure through the same contracts.

# 1. Executive Delivery Summary

This plan converts the approved product, architecture, database, and API baselines into a sequenced engineering program. The schedule is a planning baseline, not a commitment: it assumes an eight-person core team, stable access to provider test environments, and timely architecture decisions. Each milestone exits only on objective evidence, not elapsed time.

Delivery model: two-week sprints with continuous integration and milestone release gates

Critical path: foundation → identity/data/task platform → VMware adapter → integrated UI → qualification → release candidate

Provider strategy: implement one end-to-end adapter before parallelizing Workstation, AWS, and Azure

Quality strategy: tests, security, auditability, documentation, and observability are backlog work, never closing activities

Change control: new v0.1 scope requires PRD impact, estimate, dependency, risk, and gate approval

# 2. Planning Assumptions and Constraints

| Assumption | Baseline |
| --- | --- |
| Core team | 1 product lead, 1 architecture/tech lead, 3 backend/platform engineers, 2 frontend engineers, 1 QA/SDET |
| Fractional support | Security, UX, DevOps/SRE, technical writing, provider SMEs |
| Cadence | 16 two-week sprints; milestone demonstrations at gate boundaries |
| Environments | Local, CI, integration, provider sandbox/lab, staging/release candidate |
| Provider access | vCenter/ESXi lab first; Workstation endpoints; AWS test account; Azure test subscription |
| Delivery confidence | Range-based; ±25% until Milestone 3 VMware spike and broker/agent decisions close |
| Scope boundary | Start/stop/restart, discovery/inventory, tasks, audit, health, search, RBAC; PRD exclusions remain excluded |

## 2.1 Schedule controls

Do not compress security, recovery, or provider-state verification to recover schedule

Use feature flags for incomplete provider/UI capability, not for bypassing authorization

Reforecast after Milestones 2, 4, and 8 using measured throughput and defect discovery

A milestone may overlap its successor only when all predecessor interface contracts are stable

# 3. Delivery Organization and Ownership

| Role | Accountabilities |
| --- | --- |
| Product Lead | Scope, priorities, acceptance, stakeholder decisions, release approval |
| Architecture / Tech Lead | ADRs, module boundaries, design reviews, cross-cutting quality, technical risk |
| Backend / Platform | Identity, database, APIs, tasks, audit, providers, agent gateway |
| Frontend | Design system, navigation, inventory, details, task/admin workflows, accessibility |
| QA / SDET | Test strategy, automation, environments, traceability, quality evidence |
| Security | Threat model, secure design, scanning, penetration findings, risk acceptance |
| DevOps / SRE | CI/CD, deployment, telemetry, backup/restore, reliability qualification |
| UX | Research, interaction specification, accessibility, usability validation |
| Technical Writer | Install/admin/provider setup, operations, recovery, known limitations |

## 3.1 Decision rights

Product Lead owns scope and acceptance trade-offs

Tech Lead owns architecture conformity and technical gate readiness

Security owns severity classification; Product and Security jointly approve any formal risk acceptance

QA owns evidence completeness but does not independently waive requirements

Release requires Product, Engineering, QA, Security, and Operations sign-off

# 4. Repository and Solution Structure

| Path | Purpose |
| --- | --- |
| apps/web | React/TypeScript enterprise web application |
| apps/api | ASP.NET Core API host and composition root |
| apps/worker | Background task/discovery worker host |
| apps/workstation-agent | Endpoint agent service |
| modules/identity | Authentication, sessions, RBAC |
| modules/connections | Connections, secret references, health |
| modules/inventory | Canonical resources, hierarchy, search |
| modules/tasks | Task state machine, outbox, leases, idempotency |
| modules/audit | Audit and operational events |
| providers/vmware | vCenter/ESXi adapter |
| providers/aws | EC2 adapter |
| providers/azure | Azure VM adapter |
| contracts | OpenAPI, message schemas, adapter SPI, agent protocol |
| database/migrations | Ordered PostgreSQL migrations and seed data |
| tests | Unit, contract, integration, E2E, security, performance, resilience |
| deploy | Local/integration/production manifests and runbooks |
| docs | ADRs, developer, operator, provider, release documentation |

## 4.1 Engineering conventions

Trunk-based development with short-lived branches and mandatory review

Conventional versioned migrations and API/message schema compatibility checks

Code ownership by module/provider with security-sensitive reviewer rules

Feature work includes tests, telemetry, audit behavior, documentation, and threat-model updates

Generated clients/artifacts are reproducible and verified in CI

# 5. Environment and CI/CD Plan

| Stage | Required checks / outputs |
| --- | --- |
| Developer | One-command dependencies, migrations, seeded admin, mock provider, lint/unit tests |
| Pull request | Build, lint, unit, architecture tests, migration validation, OpenAPI/schema diff, SAST, secret/dependency scan |
| Integration | Ephemeral database/broker, contract/integration suites, provider mocks/sandboxes, container scan, SBOM |
| Nightly | E2E, resilience, accessibility, provider integration, migration-from-prior, backup/restore smoke |
| Milestone | Reference-scale performance, threat controls, manual exploratory, documentation verification, gate evidence |
| Release candidate | Signed immutable artifacts, provenance, SBOM, install/upgrade/restore tests, known limitations, approvals |

# 6. Estimation and Backlog Policy

Epic estimates use ideal engineering weeks and a delivery range; sprint commitments use team capacity after refinement

Stories must be independently demonstrable, testable, and traceable to a requirement/architecture contract

Provider work includes SDK research, permissions, throttling, pagination, error mapping, fixtures, sandbox testing, and documentation

No story is complete when only the happy path works

Unplanned production/release defects displace lower-priority scope; they do not silently increase capacity

## 6.1 Definition of Ready

User/technical outcome and non-goals are clear

Acceptance criteria are observable and linked to governing requirements

Dependencies, data/API changes, security impact, and telemetry are identified

Provider sandbox/test data and UX behavior are available where required

Estimate fits a sprint or is decomposed

Open decision that could invalidate work is resolved or explicitly time-boxed as a spike

## 6.2 Definition of Done

Reviewed code merged with automated tests at appropriate levels

Database/API/message changes pass compatibility and migration tests

Authorization, audit, error, redaction, and observability behaviors verified

Accessibility and supported-resolution behavior verified for UI work

Security scans show no unaccepted release-blocking finding

Operational and user documentation updated

Traceability and acceptance evidence attached; feature demonstrated in integration environment

# 7. Milestone Roadmap

| ID | Milestone | Sprint | Range | Exit outcome |
| --- | --- | --- | --- | --- |
| M0 | Program mobilization | S1 | 2 wks | Approved plan, environments/access owners, backlog and risk register |
| M1 | Engineering foundation | S1–S2 | 4 wks | Repository, local stack, CI, contracts, migration skeleton, telemetry baseline |
| M2 | Identity, RBAC, DB & API foundation | S3–S4 | 4 wks | Login/session, roles, core schemas, API conventions, secret storage |
| M3 | Tasks, audit & observability | S5–S6 | 4 wks | Durable task lifecycle, outbox, workers, audit chain, health/metrics |
| M4 | VMware vertical slice | S7–S9 | 6 wks | Connect/discover/inventory/detail/start-stop-restart/tasks/audit end-to-end |
| M5 | Unified enterprise UI | S8–S11 | 8 wks | Dashboard, hierarchy, inventory, detail, connection/admin/task UX; overlaps M4 |
| M6 | Workstation agent | S10–S12 | 6 wks | Enrollment, heartbeat, discovery, signed commands, lifecycle path |
| M7 | AWS EC2 | S11–S13 | 6 wks | Account/regions, discovery, normalized mapping, lifecycle operations |
| M8 | Azure VMs | S12–S14 | 6 wks | Subscription discovery, LRO integration, stop/deallocate, lifecycle |
| M9 | Integrated qualification | S15 | 2 wks | Security, scale, fault isolation, accessibility, recovery, docs |
| M10 | Release candidate | S16 | 2 wks | Install/upgrade/restore, signed artifacts, traceability, approvals |

Total elapsed baseline is 32 weeks because UI and later provider work overlap after stable contracts. Effort is greater than elapsed time and assumes the reference team. Reforecasting is mandatory after the VMware vertical slice.

# 8. Critical Path and Dependencies

| Predecessor | Successor | Dependency |
| --- | --- | --- |
| M0 | M1 | Repository, decision owners, provider access requests |
| M1 | M2 | CI, local stack, architecture rules, migration and contract pipeline |
| M2 | M3 | Identity, database, secrets, API conventions |
| M3 | M4 | Tasks, audit, adapter SPI, observability, error model |
| M4 | M5 completion | Real provider data/actions validate UI contracts |
| M4 | M6/M7/M8 | Adapter conformance pattern and task semantics proven |
| M6/M7/M8 | M9 | All providers pass functional and failure suites |
| M5 + M9 | M10 | Integrated UX, security, recovery, documentation evidence |

## 8.1 Critical external dependencies

Supported vCenter/ESXi and Workstation licenses/test hosts

AWS account and Azure subscription with least-privilege test identities

TLS certificates and key-management integration

Backend runtime, broker, agent transport, and deployment ADR closure

UI/UX specification delivered before M5 interaction freeze

# 9. M0 — Program Mobilization

| Backlog ID | Story / task | Owner | Estimate | Acceptance evidence |
| --- | --- | --- | --- | --- |
| IMP-0001 | Approve implementation plan and scope baseline | Product/Tech | 3d | Signed gate record; change-control process |
| IMP-0002 | Assign ADR owners and decision dates | Tech Lead | 1d | ADR tracker with evidence requirements |
| IMP-0003 | Provision provider labs and cloud test identities | Ops/Providers | 5–10d | Connectivity and least-privilege validation |
| IMP-0004 | Create requirements/backlog traceability registry | QA/Product | 3d | Every must-have PRD domain mapped |
| IMP-0005 | Create program risk, dependency, and decision registers | PM/Product | 2d | Owners, triggers, review cadence |
| IMP-0006 | Finalize team capacity and sprint calendar | Engineering | 1d | Capacity baseline and on-call/leave assumptions |

# 10. M1 — Engineering Foundation

| Backlog ID | Deliverable | Estimate | Depends | Done evidence |
| --- | --- | --- | --- | --- |
| IMP-0101 | Create monorepo/solution modules and ownership rules | 4d | M0 | Build succeeds; architecture tests |
| IMP-0102 | Local PostgreSQL, broker, API, worker, web stack | 5d | 0101 | One-command startup and health |
| IMP-0103 | CI build/test/lint and artifact packaging | 5d | 0101 | Protected PR checks |
| IMP-0104 | OpenAPI/message/migration compatibility pipeline | 5d | 0101 | Breaking-change detection |
| IMP-0105 | Structured logging, correlation, OpenTelemetry baseline | 5d | 0102 | Trace from API to worker mock |
| IMP-0106 | Security scanning, SBOM, secret detection | 4d | 0103 | Policy gates and reports |
| IMP-0107 | Test fixtures and mock provider adapter | 5d | 0102 | Deterministic discovery/action tests |
| IMP-0108 | Developer guide and contribution standards | 3d | 0101–07 | Clean-machine validation |

# 11. M2 — Identity, RBAC, Database, and API Foundation

| Backlog ID | Deliverable | Estimate | Trace |
| --- | --- | --- | --- |
| IMP-0201 | Identity/RBAC migrations and seed roles | 5d | AUTH/RBAC; DAPI 4 |
| IMP-0202 | Argon2id login, session, lockout, logout | 8d | AUTH; TADS 17 |
| IMP-0203 | Server-side permission policies and matrix tests | 6d | RBAC |
| IMP-0204 | Connection and encrypted secret schemas/services | 8d | CONN/SEC; DAPI 5 |
| IMP-0205 | Envelope encryption and key rotation spike | 5d | TADS 18 |
| IMP-0206 | Inventory core migrations/repositories | 8d | DISC/VM/INV; DAPI 6 |
| IMP-0207 | API global conventions, problem details, ETag, pagination | 7d | API; DAPI 14–15 |
| IMP-0208 | Authentication and user/role administration API | 6d | DAPI 16 |
| IMP-0209 | Connection CRUD/credential rotation API | 6d | DAPI 17 |
| IMP-0210 | Identity/security audit events and negative tests | 5d | AUD/PLATSEC |

# 12. M3 — Durable Tasks, Audit, and Observability

| Backlog ID | Deliverable | Estimate | Done evidence |
| --- | --- | --- | --- |
| IMP-0301 | Task/outbox/idempotency migrations | 6d | Constraint and migration tests |
| IMP-0302 | Task state machine and transition tests | 6d | All legal/illegal transitions |
| IMP-0303 | Broker publisher, worker claims, leases, recovery | 10d | Crash/redelivery/lease tests |
| IMP-0304 | Retry, timeout, cancellation, verification-required policies | 7d | Failure injection results |
| IMP-0305 | Append-only audit store and search API | 7d | Atomicity, authorization, redaction |
| IMP-0306 | Operational events and platform health | 6d | Component/connection health |
| IMP-0307 | Task history/detail/cancel/retry APIs | 6d | OpenAPI contract tests |
| IMP-0308 | Metrics/dashboards for API, queue, workers, tasks | 5d | Alertable telemetry |
| IMP-0309 | Backup/restore automation baseline | 5d | Successful restore smoke |

# 13. M4 — VMware vCenter/ESXi Vertical Slice

| Backlog ID | Deliverable | Estimate | Acceptance |
| --- | --- | --- | --- |
| IMP-0401 | VMware SDK/permissions/version spike | 5d | Supported interfaces and compatibility matrix |
| IMP-0402 | Connection validation, TLS, error mapping | 7d | Secret-safe success/failure cases |
| IMP-0403 | Datacenter/cluster/host/datastore/network discovery | 10d | Paged hierarchy and identity |
| IMP-0404 | VM mapping and reconciliation | 10d | Canonical fields, rename/missing behavior |
| IMP-0405 | VM inventory/detail APIs and query indexes | 7d | Reference dataset queries |
| IMP-0406 | Capability evaluation by VM state | 5d | Unsupported actions suppressed |
| IMP-0407 | Start operation through durable task | 6d | Verified final state and audit |
| IMP-0408 | Stop operation through durable task | 6d | Confirmation, timeout, verification |
| IMP-0409 | Restart operation through durable task | 6d | Provider semantics and final state |
| IMP-0410 | Throttle/outage/auth/partial-discovery tests | 8d | Fault isolation evidence |
| IMP-0411 | VMware setup and troubleshooting guide | 4d | Clean administrator validation |

## 13.1 Vertical-slice demonstration

Administrator logs in and registers a vCenter connection.

Connection test succeeds and secret is never returned.

Discovery creates a durable task and populates hierarchy and VM inventory.

Operator filters inventory and opens VM detail/capabilities.

Operator confirms start, stop, and restart actions.

Each operation continues after browser closure, verifies provider state, and produces audit history.

Connection outage degrades VMware only and yields correlated diagnostics.

# 14. M5 — Unified Enterprise UI

| Backlog ID | Deliverable | Estimate | Key quality |
| --- | --- | --- | --- |
| IMP-0501 | UI design tokens, navigation shell, light/dark modes | 8d | 1366×768 through 2560×1440 |
| IMP-0502 | Authentication/session/error/loading foundation | 6d | Accessible and secure states |
| IMP-0503 | Dashboard cards, provider distribution, recent activity | 8d | Navigable and data-freshness aware |
| IMP-0504 | Unified VM inventory table | 12d | Search/filter/sort/page/columns |
| IMP-0505 | Provider-aware infrastructure tree | 10d | Lazy navigation and contextual filtering |
| IMP-0506 | VM detail workspace and tabs | 10d | Responsive dense enterprise layout |
| IMP-0507 | State-aware actions, confirmation, task progress | 8d | No color-only state; failure recovery |
| IMP-0508 | Connections administration | 10d | Write-only credentials, test/discovery workflows |
| IMP-0509 | Tasks, events, audit, platform health views | 12d | Permission-aware, correlated drilldown |
| IMP-0510 | Users/roles/settings administration | 8d | ETag conflicts and audit |
| IMP-0511 | Accessibility and supported-browser suite | 7d | WCAG 2.1 AA core journeys |
| IMP-0512 | Usability evaluation and refinement | 5d | Admin/operator task completion |

# 15. M6 — VMware Workstation Agent

| Backlog ID | Deliverable | Estimate | Acceptance |
| --- | --- | --- | --- |
| IMP-0601 | Agent transport/enrollment/revocation spike | 7d | ADR and threat tests |
| IMP-0602 | Agent Windows service packaging and identity | 8d | Install/start/restart/uninstall |
| IMP-0603 | Heartbeat, compatibility, offline health | 7d | Server/agent version negotiation |
| IMP-0604 | Local Workstation VM discovery/mapping | 10d | Stable local identity and inventory |
| IMP-0605 | Signed command envelope and replay ledger | 8d | Expired/replayed/tampered rejection |
| IMP-0606 | Start/stop/restart command execution | 10d | Least privilege and final state |
| IMP-0607 | Reconnect, duplicate, crash, clock-skew tests | 8d | Durable and safe recovery |
| IMP-0608 | Staged signed upgrade foundation | 7d | Compatibility and rollback path |
| IMP-0609 | Agent deployment/admin troubleshooting guide | 4d | Clean endpoint validation |

# 16. M7 — AWS EC2 Adapter

| Backlog ID | Deliverable | Estimate | Acceptance |
| --- | --- | --- | --- |
| IMP-0701 | IAM role/credential/permission spike | 5d | Least-privilege policy documented |
| IMP-0702 | Account connection and regional scopes | 6d | Temporary credentials preferred |
| IMP-0703 | Paged multi-region discovery | 10d | Concurrency and checkpoints |
| IMP-0704 | EC2 canonical mapping, tags, volumes, networking | 9d | Required normalized fields |
| IMP-0705 | Start/stop/reboot task operations | 9d | State-aware verified outcomes |
| IMP-0706 | Throttling/backoff/partial-region fault tests | 7d | Provider isolation and safe retries |
| IMP-0707 | AWS setup/permissions/troubleshooting guide | 4d | Clean account validation |

# 17. M8 — Microsoft Azure VM Adapter

| Backlog ID | Deliverable | Estimate | Acceptance |
| --- | --- | --- | --- |
| IMP-0801 | Service identity/permissions/version spike | 5d | Least-privilege role documented |
| IMP-0802 | Subscription/scopes connection | 6d | Multiple subscriptions supported |
| IMP-0803 | Paged VM/resource/network/disk discovery | 10d | Resource IDs and hierarchy |
| IMP-0804 | Azure canonical mapping and tags | 9d | Required normalized fields |
| IMP-0805 | Start/stop-deallocate/restart tasks | 10d | LRO reference and final verification |
| IMP-0806 | Throttle/LRO timeout/partial-scope tests | 8d | Verification-required semantics |
| IMP-0807 | Azure setup/permissions/troubleshooting guide | 4d | Clean subscription validation |

# 18. M9 — Integrated Qualification

| Workstream | Exit evidence |
| --- | --- |
| Functional | All must-have PRD acceptance criteria pass across supported providers |
| Security | Threat actions closed; authorization/CSRF/secret/replay tests; no unaccepted Critical/High |
| Performance | 10,000-VM inventory/dashboard/task scenarios meet TADS targets |
| Reliability | Worker crash, broker restart, provider outage/throttle, database recovery, ambiguous operation |
| Recovery | Backup restore and post-outage provider reconciliation within approved RPO/RTO |
| Accessibility | WCAG 2.1 AA core journeys; keyboard, focus, contrast, status semantics |
| Compatibility | Supported provider, browser, agent, database, and deployment matrix |
| Operations | Health, metrics, logs, correlation, alerts, runbooks, known limitations |
| Documentation | Install, upgrade, provider setup, administration, backup/restore, troubleshooting |

## 18.1 Defect exit policy

Zero open severity-1 defects

Zero known unauthorized-operation or secret-exposure defects

Severity-2 defects require documented workaround and explicit release-board disposition

Flaky qualification tests are defects and cannot be hidden by retries

Provider limitations are documented, surfaced in capability behavior, and included in release notes

# 19. M10 — Release Candidate

| Backlog ID | Deliverable | Acceptance |
| --- | --- | --- |
| IMP-1001 | Build signed immutable RC artifacts and SBOM | Provenance verified |
| IMP-1002 | Clean install in reference topology | Runbook executed by nonauthor |
| IMP-1003 | Upgrade and migration rehearsal | Prior baseline → RC; compatibility evidence |
| IMP-1004 | Backup/restore and key recovery rehearsal | Approved recovery time and reconciliation |
| IMP-1005 | Release traceability package | Requirements → stories → tests → results |
| IMP-1006 | Operations handoff and alert review | Owners, dashboards, escalation, runbooks |
| IMP-1007 | Final security and license review | No release blocker |
| IMP-1008 | Product/Engineering/QA/Security/Ops approval | Signed release gate and known limitations |

# 20. Cross-Cutting Backlog

| Backlog family | Recurring requirements |
| --- | --- |
| SEC | Threat modeling, authorization matrix, secure coding, scans, SBOM, redaction, penetration findings |
| QA | Unit/contract/integration/E2E/accessibility/performance/resilience test automation and data |
| OBS | Correlation, structured logs, metrics, traces, dashboards, alerts, secret-safe diagnostics |
| DOC | Developer, API, installation, administration, provider permissions, troubleshooting, recovery, release notes |
| DATA | Migrations, indexes, query plans, retention, backup/restore, compatibility |
| UX | Interaction specs, design tokens, responsiveness, accessibility, usability evidence |
| OPS | Deployment manifests, configuration validation, certificates, maintenance/upgrade, incident runbooks |

# 21. Test Execution Matrix

| Test level | Every PR | Nightly | Milestone / RC |
| --- | --- | --- | --- |
| Unit | Yes | Yes | Yes |
| Architecture/module boundaries | Yes | Yes | Yes |
| OpenAPI/message compatibility | Yes | Yes | Yes |
| Migration from empty | Yes | Yes | Yes |
| Migration from prior release | No | Yes | Yes |
| Database/broker integration | Selected | Yes | Yes |
| Provider mock contract | Yes | Yes | Yes |
| Live provider integration | No | Scheduled | Yes |
| End-to-end UI | Smoke | Full | Full |
| Security dynamic/authorization | Selected | Full | Full + manual |
| Accessibility | Static/smoke | Automated | Automated + manual |
| Performance/resilience | No | Smoke | Reference-scale/full |
| Backup/restore | No | Smoke | Full rehearsal |

# 22. Requirements Traceability Plan

| Domain | Primary milestones |
| --- | --- |
| Authentication/RBAC/Security | M1–M3, M9–M10 |
| Connections/credentials | M2, provider milestones, M9 |
| Discovery/model/inventory/hierarchy | M2, M4–M8 |
| VM detail and lifecycle operations | M4–M8 |
| Capabilities/provider awareness | M4–M8 |
| Tasks/idempotency/audit | M3–M8 |
| Dashboard/search/UI/accessibility | M5, M9 |
| API/database contracts | M1–M3, all provider milestones |
| Performance/reliability/observability | M1, M3, M9 |
| Deployment/recovery/documentation | M1, M9–M10 |

The traceability registry links PRD requirement ID → TADS/DAPI section → backlog item → code/change set → automated/manual test → milestone result. A must-have requirement without passing evidence blocks release unless formally waived through change control.

# 23. Risk Register

| Risk | Probability / impact | Mitigation / trigger |
| --- | --- | --- |
| Provider SDK/API incompatibility | M / H | Early spikes and compatibility matrix; reforecast if unsupported versions expand |
| Broker semantics fail durability needs | M / H | M1 prototype; decide before M3 implementation |
| VMware lab/access delay | M / H | Provision in M0; mock adapter allows foundation only, not M4 exit |
| Workstation agent security complexity | H / H | Threat-driven spike, protocol tests, staged scope |
| Cloud throttling and permissions | M / M | Least-privilege policies, sandbox tests, regional budgets |
| UI starts before contracts stabilize | M / M | Mock OpenAPI first; freeze interaction contracts at M4 |
| Scope growth | H / H | PRD change control and explicit v0.1 exclusions |
| Underestimated qualification | M / H | Quality work embedded; reserve M9; track automation debt |
| Key-person/provider knowledge | M / M | Pairing, code ownership, runbooks, recorded decisions |
| Brand clearance | M / M | Keep working-brand status; avoid irreversible public launch assets |

# 24. Metrics and Reporting

| Metric | Purpose |
| --- | --- |
| Milestone burn-up by accepted story | Shows delivered scope, not activity |
| Lead/cycle time and blocked age | Detects flow and dependency problems |
| Escaped defects by severity/domain | Targets quality hotspots |
| Automated acceptance coverage by PRD ID | Measures traceability completeness |
| Build/test reliability and flaky-test rate | Protects delivery signal |
| Provider task success and verification-required rate | Measures operational correctness |
| Security finding age and recurrence | Measures risk closure quality |
| Performance trend at reference scale | Detects regression |
| Documentation/runbook validation pass rate | Measures operational readiness |

## 24.1 Governance cadence

Daily engineering coordination focused on blockers and operational risk

Weekly product/engineering backlog and dependency review

Biweekly sprint review, demo, retrospective, and risk reforecast

Milestone gate review with recorded exit evidence and decision

Monthly architecture/security review until release candidate

# 25. Change Control

Submit change with problem, requested outcome, urgency, and originating requirement.

Assess PRD/TADS/DAPI impact, dependencies, security, data/API compatibility, estimate, schedule, and test impact.

Classify as clarification, defect, scope substitution, or scope expansion.

Tech Lead and Product Lead recommend disposition; Security/Operations join when affected.

Approved change updates governing document/backlog/traceability and reforecast.

Rejected or deferred change enters post-v0.1 roadmap with rationale.

# 26. Milestone Gate Checklist

Planned acceptance outcomes demonstrated in integration/staging

Required automated and manual suites pass with evidence

No gate-blocking defect, security finding, unresolved decision, or dependency

Database/API/message changes are compatible and documented

Telemetry and audit behavior support diagnosis and attribution

Install/configuration/operation documentation for the increment is validated

Traceability is current; risks and estimates are reforecast

Product, Engineering, QA, and applicable Security/Operations owners approve exit

# 27. Program Acceptance Criteria

| Criterion | Pass condition |
| --- | --- |
| IMP-AC-001 | Every must-have PRD requirement maps to at least one backlog item and passing acceptance result. |
| IMP-AC-002 | No provider milestone exits without discovery, normalization, lifecycle, task, audit, failure, and documentation evidence. |
| IMP-AC-003 | The VMware vertical slice proves the complete production-shaped path before later adapters are accepted. |
| IMP-AC-004 | Browser closure, worker crash, provider throttling, and ambiguous operations do not cause unsafe duplicate execution or silent success. |
| IMP-AC-005 | No secret appears in client, database nonsecret fields, queues, logs, audit, errors, or test artifacts. |
| IMP-AC-006 | Reference-scale performance, recovery, accessibility, and security targets pass before RC. |
| IMP-AC-007 | Release artifacts are signed, reproducible, scanned, and accompanied by SBOM and provenance. |
| IMP-AC-008 | Install, upgrade, backup/restore, provider setup, and troubleshooting are executed from documentation by a nonauthor. |
| IMP-AC-009 | All open decisions required for v0.1 are closed or explicitly accepted as release limitations. |
| IMP-AC-010 | Release gate records approvals, residual risks, known limitations, and post-v0.1 backlog. |

# 28. Immediate First-Sprint Backlog

| Priority | Work item | Outcome |
| --- | --- | --- |
| P0 | Approve M0 decisions, ownership, capacity, and provider access | Program unblocked |
| P0 | Create repository/solution and architecture boundary tests | Buildable structure |
| P0 | Create local PostgreSQL/broker/API/worker/web environment | One-command platform |
| P0 | Establish CI build/unit/lint/security scan | Protected main branch |
| P0 | Create OpenAPI, migration, and message-contract validation | Contract discipline |
| P0 | Implement correlation and telemetry skeleton | Observable request → worker mock |
| P1 | Build deterministic mock provider adapter | Parallel backend/UI testing |
| P1 | Draft initial schema migration and identity seed | M2 head start |
| P1 | Start VMware SDK/permissions compatibility spike | Reduce critical-path risk |
| P1 | Draft Enterprise UI/UX Specification | Prepare M5 without inventing interaction contracts |

# Appendix A — Estimate Summary

| Workstream | Approximate ideal effort | Primary uncertainty |
| --- | --- | --- |
| Foundation/platform | 28–36 engineer-weeks | Broker/deployment decisions |
| Identity/data/API/tasks/audit | 38–48 engineer-weeks | Security and recovery semantics |
| VMware vertical slice | 22–30 engineer-weeks | SDK/version/lab behavior |
| Enterprise UI | 34–44 engineer-weeks | Interaction breadth and usability refinement |
| Workstation agent | 24–34 engineer-weeks | Transport, signing, endpoint variability |
| AWS EC2 | 16–22 engineer-weeks | Multi-region throttling and permissions |
| Azure VMs | 18–24 engineer-weeks | Long-running operations and resource linkage |
| Qualification/release/docs | 28–38 engineer-weeks | Defect discovery and compatibility matrix |

Effort ranges are not additive calendar duration because work overlaps across specialists. They exclude future PRD scope and assume provider environments are available. A formal staffing plan and cost forecast should be produced after M1 architecture spikes and again after M4.

# Appendix B — Definition of Program Done

All v0.1 scope is implemented or formally dispositioned

All milestone and program acceptance criteria have passing evidence

All supported providers pass a common adapter conformance suite and provider-specific qualification

Security, accessibility, performance, resilience, backup/restore, and compatibility gates pass

Signed release artifacts, SBOM, provenance, migrations, OpenAPI, and agent packages are reproducible

Administrators can install, connect providers, discover VMs, operate them, diagnose failures, and audit actions from validated documentation

Release approvals and post-v0.1 backlog are recorded

# Appendix C — Document Status

This document is a draft execution baseline governed by NUV-PRD-001, NUV-TADS-001, and NUV-DAPI-001. Estimates are planning ranges and must be reforecast with measured delivery data. Approval authorizes backlog refinement and Milestone 0–1 execution. Nuvrion remains a working brand pending formal trademark clearance.